## Project Data
Project Name | Ontology-Driven Operating System (ODOS)
Online team meeting | https://tu-berlin.zoom-x.de/j/66022239802?pwd=I409Z0ib9RwajWU4sIf7ySD1WmR0Xa.1
Production system (if any) | ...
Test system (if any) | ...
GitHub repository | https://github.com/amosproj/amos2026ws04-odos
GitHub feature board | https://github.com/orgs/amosproj/projects/112/views/2
GitHub imp-squared backlog | https://github.com/orgs/amosproj/projects/116
Position of T-shirt logo | Upper Torso Right Small
Link to logo for black T-shirt | https://github.com/amosproj/amos2026ws04-odos/blob/main/Deliverables/sprint-01/team-logo-black-shirt.svg
Link to logo for white T-shirt | https://github.com/amosproj/amos2026ws04-odos/blob/main/Deliverables/sprint-01/team-logo.svg
Additional materials | ...
Team maling list | oss-amos-proj4@lists.fau.de

## Project Team
Last Name | First Name | GitHub User Name | Email Address
Barvencik | Moritz | moritzbarv | barvencik@campus.tu-berlin.de ; barvencik.moritz@web.de
Haykır | Zeynep | zeynephaykir | z.haykir@campus.tu-berlin.de
Thomits | Nicole | NicoleT02 | nicole.thomits@fau.de
Hirschpeck | Leon | leones18 | leon.hirschpeck@fau.de
Akhlaq | Abdullah | Abdullah-Akhlaq | abdullah.akhlaq@fau.de
Haider | Muhammad Irfan | irfanhaider008 | irfan.haider@fau.de
Akram | Wasim | WasimAkramShuvo | wasim.akram@fau.de
Li | Linfeng | WindyLeev | linfeng.li@campus.tu-berlin.de

## Role Assignments
Product Owner
# | Meeting Day | Review | Planning | Software Developer | Release Manager | Scrum Master | Comment
1 | 2026-10-14 | -- | Zeynep | Everyone else | N/A | Dirk
2 | 2026-10-21 | Zeynep | Nicole | Everyone else | Moritz | Felicitas
3 | 2026-10-28 | Nicole | Zeynep | Everyone else | TBD | Felicitas
4 | 2026-11-04 | Zeynep | Nicole | Everyone else | TBD | Felicitas
5 | 2026-11-11 | Nicole | Zeynep | Everyone else | TBD | Felicitas
6 | 2026-11-18 | Zeynep | Nicole | Everyone else | TBD | Felicitas
7 | 2026-11-25 | Nicole | Zeynep | Everyone else | TBD | Felicitas | Mid-term due
8 | 2026-12-02 | Zeynep | Nicole | Everyone else | TBD | Felicitas
9 | 2026-12-09 | Nicole | Zeynep | Everyone else | TBD | Felicitas
10 | 2026-12-16 | Zeynep | Nicole | Everyone else | TBD | Felicitas
11 | 2027-01-13 | Nicole | Zeynep | Everyone else | TBD | Felicitas
12 | 2027-01-20 | Zeynep | Nicole | Everyone else | TBD | Felicitas
13 | 2027-01-27 | Nicole | Zeynep | Everyone else | TBD | Felicitas
14 | 2027-02-03 | Zeynep | Nicole | Everyone else | TBD | Felicitas | Demo day!
15 | 2027-02-10 | Nicole | Zeynep | Everyone else | TBD | Felicitas | Retrospective
Product owners, software developers, and Scrum Master are set and ideally don't change over time; the critical part is the Release Manager role you need to define here
Formulas:
Meeting Day = [Meeting Day, row above]+7

## Team Contract
Goals | Ensure everyone learns the AMOS lessons
Helping and learning from each other
Ensure happpiness with final results
Have a good team experience
Deliver an MVP and successfully complete the project
Comply with relevant standards
Meeting norms | Be punctual
Working norms | Complete adopted sprint backlog items by the end of a sprint
Decide based on consensus (everyone but one needs to agree)
Coordination norms | Communicate information intime e.g. for meetings you might miss
Communication norms | Be open and honest about what needs saying
Consideration norms | Be respectful and considerate about others
Cont. improvement norms | Regularly update the team on progress
Rewards
Sanctions | (After one warning) talk to the authorities
Signatures
Scrum Master | Dirk Riehle (for Felicitas Engelhardt)
Product owner | Nicole Thomits
Product owner | Zeynep Haykır
Software developer | Muhammad Irfan Haider
Software developer | Leon Hirschpeck
Software developer | Moritz Barvencik
Software developer | Linfeng Li
Software developer | Wasim Akram
Software developer | Abdullah Akhlaq

## Product Goal
Product Vision | Project Mission
Small and medium-sized industrial companies need software that fits their own products and processes, but they can’t afford to have it built from scratch. ODOS makes that possible. It gives them a digital twin of their product or plant that they can trust, from planning to end-of-life. Laws, standards and company rules are part of the twin, so only designs that follow them are accepted. | In this project we look for a way to turn laws and standards into rules that a computer can check. We start with two example documents, the EU Machinery Regulation and the German Musterbauordnung. We compare different options, then work on getting the rules out of PDF documents and applying them to digital twins. At the end, we give Wisdom Bridge AI a clear recommendation and, if possible, a working prototype.

## Product Glossary
Term | Definition

## Sprint Goals
Sprint # | Sprint goal
1 | Set up the team and its ways of working, and establish contact with the business partner.
2 | TBD
3 | TBD
4 | TBD
5 | TBD
6
7
8
9
10
11
12
13
14
15

## Velocity Tracking
Sprint # | Story Points Realized
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
PLEASE CREATE THE VELOCITY CHART ON A NEW TAB USING THE DATA FROM THIS TAB

## Mid-Project Release plan
Sprint | Goal | Feature Name | Est. size | Est. remaining | Real size | Real remaining
Release
Total |  |  | 0 | 0
Sprints
|  |  |  | Estimated burn-down |  | Real burn-down
1 |  |  | 0 | 0 | 0 | 0
2 |  |  | 0 | 0 | 0 | 0
3 |  |  | 0 | 0 | 0 | 0
... |  |  |  | 0 |  | 0
Features
1
2
3
PLEASE CREATE THE BURNDOWN CHART ON A NEW TAB USING THE DATA FROM THIS TAB

## Final Project Release plan
Sprint | Goal | Feature Name | Est. size | Est. remaining | Real size | Real remaining
Release
Total |  |  | 0 | 0
Sprints
|  |  |  | Estimated burn-down |  | Real burn-down
1 |  |  | 0 | 0 | 0 | 0
2 |  |  | 0 | 0 | 0 | 0
3 |  |  | 0 | 0 | 0 | 0
... |  |  |  | 0 |  | 0
Features
1
2
3
PLEASE CREATE THE BURNDOWN CHART ON A NEW TAB USING THE DATA FROM THIS TAB

## Definition of Done
# | Feature Definition of Done | Sprint Release Definition of Done | Project Release Definition of Done

## Documentation
Type | Link / reference

## Bill of Materials
# | Context | Name | Version | License | Comment

## Planning Poker
Last Name | First Name | Value
Barvencik | Moritz | 0 | 0 | OK
Haykır | Zeynep | 0
Thomits | Nicole
Hirschpeck | Leon
Akhlaq | Abdullah |  | 0 | No size
Haider | Muhammad Irfan |  | 1 | Trivial size
Akram | Wasim |  | 2 | Small size
Li | Linfeng |  | 3 | Medium size
|  |  | 5 | Large size
|  |  | 8 | Very large size
|  |  | 13 | Too large (size)
How to play planning poker
1. Everyone type their number into their value field, don't hit return yet
2. Someone, perhaps a product owner, count down 3.. 2.. 1..
3. Then, everyone hit return to submit their value